## Sheet1
Prio | Kickoff/Design
| Screen / Feature Name(s) | Feature Name | File (if relevant) | Location | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
1 | Documentation | Technical Design Document |  |  | Marissa
1 | Project Setup | Setup | Project Plan (Google sheet) | Google docs | Team
1 | Data Model- Shopping List | Data Model | 8.2.2 of Team 2 TDD.doc | Google docs | Spencer/Ethan
1 | Data Model - Shopping List Item | Data Model | 8.2.3 of Team 2 TDD.doc | Google docs | Spencer/Ethan
1 | Data Model - Note | Data Model | 8.2.4 of Team 2 TDD.doc | Google docs | Spencer/Ethan
1.5 | ShoppingList bean |  | ShoppingList.java (8.2.2) | com.slt2.beans
1.5 | Add New Shopping List Interface | Adding Lists | createShoppingList.html | src/main/resources/templates/shoppinglist
1.5 | Add New Shopping List Functionality | Adding Lists | ShoppingListController.java | .com.slt2.shoppinglist
1.5 | Persist list to database | List to database | ShoppingListRepository.java | com.slt2.repository
1.5 | Show shopping list | Needs to go to view list of items | shopping_list_view.html | src/main/resources/templates/shoppinglist
1.5 | Delete shopping list | Delete (clear) list | ShoppingListController.java | .com.slt2.shoppinglist
2 | Item bean |  | Item.java (8.2.3 from TDD model) | com.slt2.beans
2 | Add New Items Interface | Adding Items | item_create.html | src/main/resources/templates/items
2 | Add New Items Functionality (methods in IC.java) | Adding Items | ItemController.java | .com.slt2.item
2 | Select Item priority (1, 2, 3) | Select Item Priorty | button in item_create.html
2 | Persist items to database (methods in IC.java) | Items to database | ItemRepository.java | com.slt2.repository
2 | Check off items (delete items) interface | Check off items | button on shopping_list_view.html | src/main/resources/templates/items
2 | Check off items (delete items) functionality | Clear items (Delete) | ItemController.java | .com.slt2.item
3 | Ordering of items (?) | Ordering of items (add to shopping list?) | Service/DAO/Controller?
3 | Sorting of Items | Sorting of items (alphabetically) | Service/DAO/Controller?
3 | Delete Individual Items | Delete Items | Row 24
3 | Edit items Interface | Edit items | itemItem.html
3 | Edit items Functionality | Edit items | ItemController.java
3 | Add notes to items | Add notes | ???
4 | User
4 | User bean |  | User.java (8.2.2 in TDD)
4 | Register button on log-in page | button that leads to user registration form (create_user.html) | login.html
4 | Register/Add New User Interface | create new user (form) | create_user.html
4 | Register/Add New User | Adds user | UserController.java
4 | Persist users to database (methods in UC.java) | Persist user to database | UserRepository.java
4 | User profile | view user profile | userprofile.html
4 | Multiple User | Multiple users | (Rows 36-41)
4 | 8.3.0 Home Page |  | home.html (either login.html or shopping_list_view.html, depending on whether user is currently logged in. We don't have to take it to this level of complexity. | src/main/resources
4 | - 8.3.0.1 Log in interface | email & password input | login.html | src/main/resources
4 | - 8.3.0.10 Log-in/Email Authorization functionality (password authorization w email) | password authentication | EmailService.java
4 | logout | logout | button on userprofile.html
4 | Grouping of Lists (?) | Grouping of lists | don't understand how lists can be grouped
4 | List Template | List Template | basic.html | src/main/resources/templates
4 | Web API | API | ShoppingList.doc
4 | Developer Portal | Dev portal
Need CreatedUtc and Modified UTC for ShoppingList, ShoppingLIstItem, and Note
2 | Deployment | Deploy | Azure, Heroku, AWS tbd
3
3 | Apply Design Template | Design | basic.html
2/Gold? | Design testing plan | Design | Process_Test_Plan.doc
2 | Testing | Test | jUnit
| Design | project plan | File (if relevant)
8.3 User Interface (UI)
| 8.3.0 Home Page | home | home.html | src/main/resources
4 | - 8.3.0.1 Log in interface | email & password input | login.html | src/main/resources
4 | - 8.3.0.10 Log-in functionality (password authorization w email) | password authentication | EmailService.java
4 | - 8.3.0.1 Create new user |  |  | com.users.service
| Name |  |  |  | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
| Design |  |  |  | Team | Project Plan Document | 2016-11-29 | 2016-11-29 | 2016-11-29
DB structure
Site layout
User experience
Work with EFA to gather requirements and estabilish metrics
Create site design based on collected requirements
Develop site design proposal for EFA review and approval
Present written status at weekly meeting
| Build Phase |  |  |  | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
Data Model- Shopping List
Data Model - Shopping List Item
Data Model - Note
Add New Items Functionality
Persist items to database
Check off items (remove items)
Ordering of items (?)
Sorting of Items
Delete Individual Items
Edit items
Add notes to items
Multiple User
Login and Authorization
Grouping of Lists (?)
List Template
Web API
Developer Portal
Deployment
Apply Design Template
Testing (See more in Testing section below)
- Vendor will complete all coding for approved site design
- Vendor will provide EFA with a detailed testing plan
- Vendor will include all content provided by EFA on redesigned web site
- Vendor will conduct testing
- Vendor will resolve any coding and site issues identified in testing
- Vendor will compile a testing report to present to EFA for review/approval
| Implementation Phase |  |  |  | Owner | Notes | TImeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
- Vendor will implement the newly redesigned web site on EFA servers
- Vendor will begin providing 24x7 web site support at this point forward until the end of the period of performance
- Present written status at weekly meeting
| Training Phase |  |  |  | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
- Vendor will provide training in accordance with approved training plan provided in the kickoff
- Present written status at weekly meeting
| Testing |  |  |  | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
Design testing cases/testing plan
Define test cases
Identify testers
Perform test cases
Development
| Project Handoff/Closure: |  |  |  | Owner | Notes | Timeline Best Case Scenario (done by 12/07/16) | Timeline Most Likely Scenario (done by 12/10/16) | Timeline Worst Case Scenario (done by 12/13/16 or not at all!)
- Vendor will provide EFA with all documentation in accordance with the approved project plan
- Vendor will present project closure report to EFA for review and approval
- Vendor will complete the project requirements checklist showing that all project tasks have been completed
- Vendor will conclude 24x7 web support at 11:59pm on the final day of the period of performance
- Present written status at weekly meeting